## Planning
	wie	Manuel Breugelmans
	wat	Planning Tsmells-Stats
	opgesteld	07-10-12
	laatste wijziging	07-12-19

	Description			Mijlpaal	#dagen	start	eind	pre
1.1	Requirements capturing			Interview verslag	0	# reeds voltooid		-
1.2	Verdiepen probleemdomein			Samenvatting referenties	7	07-10-08	07-10-15	1.1
1.3	RML & Crocopat intro			Code artefacts	3	07-10-15	07-10-18	-
1.4	Opzetten (output-)test framework			Python testframe	3	07-10-19	07-10-22	1.3
2.1	Mystery Guest			Tests & RML script	7	07-10-22	07-10-29	1.*
2.2	Lazy Test			Tests & RML script	7	07-10-29	07-11-05	1.*
2.x	Extra			2.1, 2.2	7	07-11-06	07-11-13
2.3	Assertion Roulette & Assertionless			Tests & RML script	3	07-11-14	07-11-17	1.*
2.4	Sensitive Equality			Tests & RML script	3	07-11-18	07-11-21	1.*
2.5.1	Conditional herkenning CDIF			Parser uitbreiding	7	07-11-22	07-11-29	1.*
2.5.2	Guarded Tests			Tests & RML script	7	07-11-30	07-12-07	1.*, 2.5.1
2.6	For Testers Only			Tests & RML script	3	07-12-08	07-12-11	1.*
2.7	Indirect Testing			Tests & RML script	14	07-12-12	07-12-26	1.*

2.8	Code Duplication			Tests & RML script	7	2e sem		1.*

## Pertt
wie	Manuel Breugelmans
wat	Pertt Tsmells-Stats
opgesteld	07-10-12
laatste wijziging	07-10-13
			Pertt Constraints

## Risico Analyse
	wie	Manuel Breugelmans
	wat	Risico Tsmells-Stats
	opgesteld	07-10-12
	laatste wijziging	07-10-13

	Description			OT	LT	PT	ET	S			SP		WC Delay	Path
1.1	Requirements capturing			0	0	0	0	0	0
1.2	Verdiepen probleemdomein			7	7	7	7	0	0	0	0	0	0	1.1
1.3	RML & Crocopat intro			3	3	3	3	0	0	0	0	0	0	1.1,1.2
1.4	Opzetten (output-)test framework			3	3	3	3	0	0	0	0	0	0	1.1,1.2,1.3
2.1	Mystery Guest			3	7	10	6.83	1.17	1.36	0	0	3	3	1.1,1.2,1.3,1.4
2.2	Lazy Test			3	7	10	6.83	1.17	1.36	1.36	1.17	3	6	1.*,2.1
2.3	Assertion Roulette & Assertionless			1	3	5	3	0.67	0.44	2.72	1.65	2	8	1.*,2.1,2.2
2.4	Sensitive Equality			3	3	3	3	0	0	3.17	1.78	0	8	1.*,2.1,2.2,2.3
2.5.1	Conditional herkenning CDIF			4	7	10	7	1	1	3.17	1.78	3	11	1.*,2.1,2.2,2.3,2.4
2.5.2	Guarded Tests			2	7	7	6.17	0.83	0.69	4.17	2.04	0	11	1.*,2.1,2.2,2.3,2.4,2.5.1
2.6	Indirect Testing			10	14	17	13.83	1.17	1.36	4.86	2.2	3	14	1.*,2.1,2.2,2.3,2.4,2.5.1,2.5.2
2.7	Code Duplication			10	14	16	13.67	1	1	6.22	2.49	2	16	1.*,2.1,2.2,2.3,2.4,2.5.1,2.5.2,2.6
2.8	For Testers Only			3	3	5	3.33	0.33	0.11	7.22	2.69	2	18	1.*,2.1,2.2,2.3,2.4,2.5.1,2.5.2,2.6,2.7
Einde							7.33	2.71		18	1.*,2.*